# Lenskart IdP — High-Availability Architecture on Kubernetes (AWS EKS)

Architecture, Risk Analysis & Implementation Guide

DevOps — Lenskart

July 28, 2026

Table of Contents

# PART I — Architecture & Risk Analysis

Target: idp.lenskart.com — enterprise SAML/OIDC identity provider, SSO, and identity lifecycle governance.

This document is written against the current codebase (@lenskart/lilg), not a generic reference architecture. Every recommendation below ties back to something observed in docker-compose.prod.yml, src/config.ts, src/index.ts, src/api/health.ts, src/services/outbox-worker.ts, src/services/saml-auto-keys.ts, and src/db/migrate.ts.

## 1. Current state (single point of failure inventory)

Today: one host (pam-2), one docker-compose stack, no orchestration.

| Component | Today | Failure mode |
| --- | --- | --- |
| lilg-api | 1 container | Host reboot/crash = full IdP outage — every SP login and admin console goes down |
| lilg-worker | 1 container | Outbox stalls silently; HRMS/Google/Zoho/AD provisioning backs up |
| MySQL | 1 container, local volume | Data loss risk on disk failure; no failover |
| Redis | 1 container, local volume | Sessions and MFA challenge state lost on restart |
| SAML signing keys | Written to local disk (SAML_KEY_DIR) | Tied to host; not replicated |
| TLS | Cloudflare orange-cloud → host :80/:443, optional ACME webroot | Single origin, single cert store |
| Deploy | ssh pam-2 + git reset --hard + docker-compose | Manual, no rolling update, no rollback automation |

Everything below addresses each row.

## 2. Target topology (AWS EKS, multi-AZ)

Cloudflare (DNS/WAF) → AWS ALB (Multi-AZ, ACM/Cloudflare TLS)
        → EKS cluster, node groups spread across 3 AZs
              → Deployment: lilg-api   (N replicas, HPA, PDB, topology spread)
              → Deployment: lilg-worker (2–3 replicas, Redis leader-elected)
        → RDS MySQL 8 (Multi-AZ)  |  ElastiCache Redis (Multi-AZ)  |  AWS SQS  |  Secrets Manager

See the diagram above for the visual. The rest of this doc fills in the reasoning per tier.

## 3. Compute tier — lilg-api and lilg-worker as Deployments

Why these two stay separate Deployments: they already run as separate processes/containers in docker-compose.yml (lilg-api vs. node dist/services/outbox-worker.js), and they scale differently — lilg-api scales with login traffic, lilg-worker scales with outbox queue depth.

lilg-api: - replicas: 3 minimum (one per AZ), HorizontalPodAutoscaler on CPU (60–70%) or a custom metric off lilg_db_pool_queued / request rate from the existing /metrics endpoint. - PodDisruptionBudget minAvailable: 2 so cluster upgrades/node drains never take the IdP fully down. - topologySpreadConstraints (or pod anti-affinity) keyed on topology.kubernetes.io/zone so replicas don’t collapse onto one AZ. - Probes map directly onto endpoints that already exist in src/api/health.ts — no app changes needed: - livenessProbe → GET /healthz (always 200 if process is up) - readinessProbe → GET /readyz (checks DB + Redis, returns 503 if either is down — exactly what you want gating traffic) - startupProbe → also /readyz, with a longer failureThreshold to cover first-boot migration time - Rolling update: maxUnavailable: 0, maxSurge: 1 (or 25%). Safe because sessions aren’t in-process (see §5) — no connection draining choreography needed beyond the graceful shutdown already implemented in src/index.ts (SIGTERM/SIGINT → server.close() → 30s forced-exit timeout). That code is already container/K8s-ready; just set terminationGracePeriodSeconds: 35 to give it room.

lilg-worker: - replicas: 2–3. This is safe today without any code change: src/services/outbox-worker.ts already implements Redis SET NX PX leader election (idp:outbox:leader) plus a per-system concurrency semaphore. Only one replica actively drains the outbox at a time; if it dies, the lock TTL expires and another replica takes over. Deploy multiple replicas purely for failover speed, not throughput. - No externally-facing Service needed — internal only. - Same liveness probe pattern isn’t available out of the box (no HTTP server in the worker process) — add a simple TCP or exec probe (e.g., a lockfile/heartbeat write) if you want K8s to restart a wedged worker; not blocking for initial HA rollout.

## 4. Data tier — managed AWS vs. in-cluster HA

You asked to cover both. Trade-offs:

|  | Managed (RDS + ElastiCache) | In-cluster (Percona Operator + Redis Sentinel/Operator) |
| --- | --- | --- |
| MySQL HA | RDS Multi-AZ — automatic failover (~60–120s), synchronous standby, automated backups + PITR | Percona XtraDB Cluster or MySQL InnoDB ClusterSet operator — Galera/group replication inside EKS; you own backup automation, failover tuning, storage class (EBS gp3, ReadWriteOnce per replica) |
| Redis HA | ElastiCache replication group, Multi-AZ auto-failover, encryption at rest/in transit built in | Redis Operator (e.g. Bitnami/Spotahome) running Sentinel or Redis Cluster mode as StatefulSets; you manage quorum, persistence (AOF/RDB on PVs), upgrades |
| Ops burden | Low — AWS handles patching, failover, backups | High — you run the operator, monitor quorum health, handle split-brain scenarios |
| Cost | AWS service pricing, no extra compute for DB pods | Cheaper at scale if you already over-provision EKS nodes, but real ops time cost |
| Latency | Cross-service (RDS/ElastiCache endpoints), typically same-VPC, negligible | In-cluster, marginally lower latency |
| Fit for an IdP | Recommended. This is the identity provider for the whole company — MySQL and Redis outages here mean company-wide login outage. Minimizing operational surface area matters more than the cost delta. | Reasonable if there’s an existing platform team already running these operators for other workloads and wants one operational model everywhere. |

Recommendation: RDS MySQL Multi-AZ + ElastiCache Redis Multi-AZ as the default. If there’s an existing in-cluster data platform (Percona/Redis operators already run for other services), reusing it is defensible — just budget real SRE time for quorum/failover testing before cutover, since this is higher blast-radius than a typical stateless service outage.

Either way: DB_HOST / REDIS_URL in src/config.ts are already just connection strings — no code change required to point at RDS/ElastiCache endpoints vs. in-cluster Services.

One sizing note: mysql2 pool size × lilg-api replica count must stay under RDS max_connections (and leave headroom for lilg-worker and admin tooling). Check the current pool config in src/db/connection.ts before setting HPA maxReplicas.

## 5. Sessions — already stateless-friendly

ARCHITECTURE.md §5.2: sessions are stored in MySQL (lilg_sessions) and cached in Redis (idp:session:<id>), not in-process. This is the single biggest thing already working in your favor for K8s: no session affinity / sticky sessions needed at the ALB or Ingress. Any pod can serve any request. Don’t add IngressAffinity/cookie-based routing — it would be pure overhead here.

## 6. SAML signing keys — the one thing that will break silently at N>1 replicas

### 6.1 Exact code path

src/services/saml-auto-keys.ts, ensureSamlKeys():

- Line 70–72: if both SAML_IDP_PRIVATE_KEY_PEM and SAML_IDP_CERT_PEM are already set in the environment, return immediately — nothing else in this function runs.

- Line 75–98: otherwise, look for persisted key/cert files on local disk at SAML_KEY_DIR (default /app/data/saml). If found and the cert has >30 days validity left, load them into process.env and return.

- Line 101+: otherwise, generate a brand-new RSA-2048 self-signed cert (3-year validity), write it to those two files on local disk, and inject it into process.env.

This is designed for exactly one long-lived container on one host with a persistent volume — which is what pam-2 is today. It was never designed for N interchangeable, ephemeral pods.

### 6.2 Why it breaks with multiple replicas

Kubernetes pods have ephemeral root filesystems by default (no volume = nothing survives a restart, and nothing is shared between pods regardless). Walk through a 3-replica rollout with no SAML_IDP_PRIVATE_KEY_PEM/CERT_PEM env vars set:

- Pod A boots, finds no persisted files, generates cert A, starts serving.

- Pod B boots (no shared disk), finds no persisted files either, generates cert B — a completely different keypair and fingerprint.

- Pod C generates cert C.

Now /saml/metadata returns a different certificate depending which pod the ALB happens to route a given request to. Every relying party (Google Workspace, Zoho, any SAML SP registered against this IdP) pins the certificate fingerprint it saw when the SP was configured. Whichever pod’s fingerprint got registered, the other two pods’ signed assertions will fail signature validation at the SP. Because routing is round-robin/least-connections, this doesn’t look like a clean outage — it looks like SSO working for some logins and silently failing for others, correlated with nothing obvious from the user’s side. That’s a much harder incident to diagnose than a hard failure.

Note that a shared ReadWriteMany volume (EFS) only half-fixes this: on a cold start where the file doesn’t exist yet, two pods booting at the same instant can still both hit the “no file found” branch simultaneously and both write competing cert files, with whichever write lands last silently winning on disk while the other pod keeps running with the cert it already loaded into memory. It’s the same class of race as the migration issue in §7 — a shared volume removes the steady-state divergence but not the cold-start race.

### 6.3 The fix

Generate the cert once, store it centrally, inject it as configuration — never let the app generate it per pod in this environment.

- Generate a keypair/cert once — either let ensureSamlKeys() create one locally and pull the two PEM files out, or use openssl req -x509 -newkey rsa:2048 -nodes -keyout saml.key -out saml.crt -days 1095 -subj "/CN=idp.lenskart.com/O=Lenskart IdP/OU=Identity/C=IN" if you want explicit control over validity/subject.

- Store both PEM strings in AWS Secrets Manager (e.g. one secret lilg/saml-signing-cert with privateKeyPem / certPem fields). You already depend on @aws-sdk/client-secrets-manager in package.json, so this isn’t a new tool in the stack — it’s already assumed to be there.

- Sync that secret into a Kubernetes Secret (lilg-saml-keys) via External Secrets Operator, then mount its keys as SAML_IDP_PRIVATE_KEY_PEM / SAML_IDP_CERT_PEM env vars on the lilg-api Deployment (envFrom.secretRef or explicit valueFrom.secretKeyRef).

- Because of the short-circuit at line 70–72, every pod that boots with those two env vars set skips key generation entirely and loads the identical cert — zero code changes required.

- Keep saml-auto-keys.ts as-is for local dev / docker-compose.dev.yml, where single-container auto-generation is fine. Just make sure the K8s manifests for every real environment always set both env vars so the auto-gen branch is unreachable there.

- Rotation is now a deliberate, out-of-band operation instead of a silent per-pod side effect: when the cert nears expiry, generate a new one, update the Secrets Manager entry, roll the Deployment — but budget time to update the fingerprint at every SP (Google Workspace, Zoho, etc.), since that’s an external coordination step, not just a Kubernetes one.

## 7. Migrations — no distributed lock today

### 7.1 Exact mechanics

src/index.ts line 310 calls await runMigrations() inside main(), before the HTTP server starts listening — every pod runs this on every boot. Inside src/db/migrate.ts, runMigrations():

- Opens its own dedicated mysql.createConnection() (retrying up to DB_CONNECT_RETRIES times if MySQL isn’t reachable yet).

- ensureTrackingTable() — CREATE TABLE IF NOT EXISTS lilg_schema_migrations.

- SELECT name, checksum FROM lilg_schema_migrations — builds an in-memory map of what’s already applied.

- Loops over every .sql file in migrations/ in sorted order; for each one not in that map, calls applyMigrationSql() (runs the file’s SQL as a batch, with a compatibility fallback that replays it statement-by-statement for older MySQL variants that reject ADD COLUMN IF NOT EXISTS), then INSERTs a tracking row.

There is no GET_LOCK, no advisory lock, and no transaction wrapping steps 3–4 (a transaction wouldn’t fully help anyway — MySQL DDL statements like ALTER TABLE/CREATE TABLE auto-commit implicitly regardless of any surrounding transaction). This is a textbook check-then-act race: step 3 (read “what’s applied”) and step 4 (apply + record) are two separate round-trips with no lock holding them together.

### 7.2 Why it’s fine today and won’t be at N replicas

With exactly one lilg-api container (today’s docker-compose reality), there’s only ever one caller, so the race never has a second participant. In Kubernetes, any of the following put two or more pods through runMigrations() within milliseconds of each other, all reading the same “nothing applied yet” snapshot: a rolling deploy with maxSurge > 0 bringing up new pods before old ones terminate, a kubectl apply/Helm install bringing all replicas up cold at once, an HPA scale-up event, or — worst case — a full cluster/disaster-recovery restart where all pods start simultaneously during an actual incident.

Concretely, if two pods both see a given migration as pending and both call applyMigrationSql() on it concurrently:

- MySQL 8 serializes conflicting DDL via metadata locks, so the second pod’s statement blocks behind the first’s, then typically surfaces as something like “Duplicate column name” or a lock-wait timeout once it’s unblocked.

- That error propagates out of applyMigrationSql(), is logged as 'Migration failed — aborting startup', and rethrown.

- Back in index.ts, that becomes logger.fatal(...) + process.exit(1) — the pod crash-loops, even though the migration may have already succeeded via the other pod.

- With maxUnavailable: 0, this is contained (old pods keep serving while the bad new pod loops and eventually alerts) — annoying but not an outage. In a full simultaneous restart during an incident, though, you can end up with multiple pods crash-looping against each other until they happen to serialize by luck, which delays the whole IdP coming back up at exactly the moment you can least afford it.

- There’s also a subtler risk: the statement-by-statement compatibility retry path (added specifically because some MySQL variants reject ADD COLUMN IF NOT EXISTS) interleaving with another connection’s single-batch attempt on the same ALTER TABLE is a genuinely messier failure mode than a clean duplicate-key error, since it’s operating statement-by-statement rather than atomically.

### 7.3 Fix options

Option A — recommended: move migrations out of the pod boot path entirely.

- Add a small CLI entrypoint that just calls runMigrations() and exits (e.g. node dist/db/migrate-cli.js, or reuse the existing compiled migrate.js with a thin wrapper).

- Run it as a Kubernetes Job (or a Helm pre-upgrade/pre-install hook, which Helm natively sequences before the Deployment’s new ReplicaSet rolls out) using the same container image, with a sane backoffLimit and activeDeadlineSeconds.

- Add one new boolean env var (zod-validated in config.ts, e.g. SKIP_MIGRATIONS_ON_BOOT) and gate the await runMigrations() call at index.ts:310 behind it — set true on the lilg-api/lilg-worker Deployments, leave it unset (false) only on the Job. This is the one code change this option needs.

- For Argo CD instead of Helm, the equivalent is a PreSync hook / sync-wave ordering the migration Job before the Deployment sync.

Option B — smaller diff, keeps “runs on every boot” model: add a real distributed lock.

- Right after opening the connection in runMigrations() (after the retry loop, before ensureTrackingTable), call SELECT GET_LOCK('lilg_migrations', <timeout_seconds>). Wrap the existing body in try { ... } finally { await conn.query("SELECT RELEASE_LOCK('lilg_migrations')"); await conn.end(); } — or rely on conn.end() closing the session, which implicitly releases the lock, since GET_LOCK is already scoped to runMigrations()’s dedicated connection.

- Every pod still attempts migrations on every boot, but now they serialize: the first pod to acquire the lock runs the check-and-apply cycle to completion; every other pod blocks on GET_LOCK until it’s released, then re-runs its own check and finds everything already applied (a harmless no-op).

- This is a same-file, ~5 line change and doesn’t require any new Job/Helm-hook plumbing — a reasonable stopgap if you want to scale to multiple replicas sooner and add the Job-based approach later.

Recommendation: do both — they’re not mutually exclusive, and B is nearly free once you’re touching this file.

- Ship Option A (Job/Helm pre-upgrade hook + SKIP_MIGRATIONS_ON_BOOT) as the primary mechanism. It gives you a single, visible, blocking step per deploy — if the migration fails, the rollout stops before any new pod with a mismatched schema expectation goes live. That property (fail the deploy, not the running fleet) is what you actually want for an IdP, and it’s the standard pattern for a reason.

- Add Option B’s GET_LOCK in migrate.ts anyway, as defense-in-depth, not as the primary mechanism. It’s a ~5 line change and it protects you from the scenarios Option A alone doesn’t fully cover: someone forgets to set SKIP_MIGRATIONS_ON_BOOT on a new pod template, an old Job and a new Job overlap during a fast-follow deploy, or a local/staging environment still runs multiple docker-compose instances against the same DB by mistake. Belt-and-suspenders costs almost nothing here and removes an entire class of “someone misconfigured one flag” incidents.

If you only have bandwidth for one right now: do the Job first (§7.3 Option A) — it’s the one that actually prevents a bad migration from reaching production traffic, not just the one that prevents pods from racing each other.

## 7b. Second-pass audit — other things that change at N>1 replicas

A re-review of the codebase surfaced four more findings beyond §6/§7. None block the first HA deploy the way §6/§7 do, but two are security-relevant for an IdP.

### 7b.1 OIDC signing keys — same disease as SAML keys, mostly cured by the same fix

src/oidc/keys.ts (ensureOidcKeys(), called at index.ts:323) mirrors the SAML auto-key pattern: prefer configured key → fall back to disk (OIDC_KEY_DIR/SAML_KEY_DIR) → auto-generate RSA-2048 per process and persist to local disk. Per-pod generation would mean each pod publishes a different JWKS (kid + key), so ID tokens signed by pod A fail verification against the JWKS fetched from pod B.

The saving grace: when SAML is enabled and configured, OIDC reuses the SAML IdP signing key (lines 65–68). So the §6 fix — injecting SAML_IDP_PRIVATE_KEY_PEM via Secret — automatically fixes OIDC too. Just verify isSamlEnabled() is true in prod config; if you ever run OIDC without SAML, inject a dedicated OIDC key the same way instead of relying on the disk-persist path.

### 7b.2 Login rate limiting is per-pod in-memory — weakens brute-force protection ×N

src/auth/rate-limit.ts keeps its token buckets in an in-process Map (line 14) with a setInterval evictor. With 3 replicas behind round-robin, an attacker’s attempts spread across pods, so the effective brute-force budget is ~3× the configured limit — and retries that should be blocked succeed when they land on a fresh pod. For an IdP this is worth fixing near-term: back the buckets with Redis (INCR + PEXPIRE, or a Lua token bucket — the ioredis client and the semaphore pattern already exist in outbox-worker.ts). Until then, treat configured limits as “per pod” and set them accordingly.

### 7b.3 In-process schedulers in the API will run N times concurrently

index.ts:335–337 starts three background schedulers inside every API pod:

| Scheduler | Interval | N-replica effect |
| --- | --- | --- |
| startAttendanceIgaScheduler (attendance-iga/scheduler.ts) | 60s tick | Duplicate pipeline runs — the runningByConfig guard is an in-process Set, invisible to other pods. configIsDue() re-reads DB state, which narrows but doesn’t close the race: two pods ticking in the same minute both see “due” and both run. |
| startAccessRequestExpiryScheduler (access-request-expiry.ts) | 5 min sweep | Concurrent sweeps of the same stale rows — likely idempotent-ish but racy, and duplicate log/audit noise. |
| startConnectorHealthScheduler (connector-health.ts) | periodic tick | N× redundant health probes against Google/Zoho/AD — wasteful API-quota burn, no lock found in the file. |

Fix: wrap each tick in the same Redis SET NX PX lock pattern the outbox worker already uses (e.g. idp:sched:<name>:lock with TTL ≈ interval) — small, mechanical change, one key per scheduler. Alternatively move all three into the lilg-worker process behind its existing leader election, which centralizes “singleton background work” in one place at the cost of a slightly larger refactor.

### 7b.4 RADIUS UDP listener — needs special handling if enabled in prod

startRadiusUdpServer() (radius-udp.ts) is optional (RADIUS_UDP_ENABLED=true). If used in prod: UDP doesn’t go through the ALB — it needs an NLB with a UDP listener via a separate Service. And since clients are identified by source IP (findRadiusClient(null, rinfo.address)), the Service must preserve it (externalTrafficPolicy: Local on the NLB). If RADIUS stays disabled in prod, just note it and move on.

### 7b.5 Minor notes

- /metrics counts sessions via redis.keys('idp:session:*') — KEYS is O(N) and blocks Redis; on a busy shared ElastiCache node switch to SCAN (or a counter). Low priority at current scale.

- The portal-HTTPS path (index.ts:344–379, cert loaded from general_settings at boot) should be left disabled on K8s — TLS terminates at the ALB (§8), and a DB-loaded cert read once per pod boot adds a second, divergence-prone cert store for no benefit.

## 8. Networking / TLS

Current setup: Cloudflare orange-cloud → single origin on host :80/:443, with an optional ACME webroot (/app/acme-webroot) for cert issuance directly on the app.

For K8s: terminate TLS before the app, at the AWS ALB (via the AWS Load Balancer Controller + ACM certificate) or by keeping Cloudflare in Full (strict) mode pointed at the ALB. Either way, drop the app’s ACME-webroot code path in this environment — it assumes a single, disk-persistent origin, which doesn’t hold across replicas without shared storage, and you don’t need it once ALB/Cloudflare handles TLS. Keep TRUST_PROXY=true and COOKIE_SECURE=true (already the correct prod values per docker-compose.prod.yml) so the app trusts the X-Forwarded-* headers from the ALB/Cloudflare chain — this also feeds getClientIp() for session IP attribution (ARCHITECTURE.md §5.2), so don’t skip it.

## 9. Secrets & config

Move .env (currently gitignored, hand-maintained on pam-2) to:

- K8s Secret (or External Secrets Operator + AWS Secrets Manager, reusing the existing @aws-sdk/client-secrets-manager dependency) for: SESSION_SECRET, MASTER_ADMIN_EMAIL/MASTER_ADMIN_PASSWORD, DB credentials, SAML_IDP_PRIVATE_KEY_PEM/CERT_PEM, Google/Zoho/AD adapter credentials.

- ConfigMap for non-sensitive values: PUBLIC_BASE_URL, SAML_IDP_BASE_URL, SAML_IDP_ENTITY_ID, feature-level env vars.

src/config.ts already zod-validates all of this at startup — misconfigured Secrets/ConfigMaps will fail fast and loudly (pod stuck in CrashLoopBackOff with a clear validation error), which is the behavior you want.

## 10. Messaging (SQS) — already cloud-native, no change needed

SQS_HRMS_EVENTS_URL / SQS_CELERY_BROKER_URL already point at real AWS SQS in production (docker-compose.prod.yml doesn’t override AWS_ENDPOINT_URL, so it only points at LocalStack in the dev compose file). SQS is multi-AZ by design — nothing to add here beyond making sure the EKS node/pod IAM role (via IRSA — IAM Roles for Service Accounts) has queue permissions, replacing whatever credential mechanism pam-2 uses today.

## 11. Observability

src/api/health.ts already exposes a Prometheus-format /metrics endpoint (protected by x-internal-token header), covering: - lilg_outbox_queue_depth by status — alert on this to catch a stalled worker before users notice provisioning delays. - lilg_active_sessions — useful for anomaly detection (sudden spike/drop). - lilg_db_pool_total / _free / _queued — direct signal for connection pool exhaustion, which is exactly the failure mode to watch when scaling lilg-api replicas against a fixed RDS max_connections. - lilg_employee_state_count — business-metric side effect, not infra, but free.

Wire this into kube-prometheus-stack via a ServiceMonitor (with the internal token as a bearer/custom header in the scrape config) instead of building new instrumentation.

## 12. Pre-cutover checklist

In priority order (top two are correctness issues, not just hardening):

- SAML keys: inject SAML_IDP_PRIVATE_KEY_PEM/CERT_PEM via Secret — do not rely on per-pod auto-generation (§6).

- Migrations: move to a one-shot Job or add GET_LOCK (§7).

- Confirm mysql2 pool size × max lilg-api replicas stays under RDS max_connections (§4).

- Decide managed vs. in-cluster data tier (§4) and provision accordingly.

- Stand up External Secrets Operator (or plain K8s Secrets) for .env → Secret/ConfigMap migration (§9).

- AWS Load Balancer Controller + ACM (or Cloudflare Full-strict) for TLS; retire the ACME-webroot path (§8).

- IRSA for SQS + Secrets Manager access, replacing whatever AWS creds mechanism is used on pam-2 today.

- Move login rate limiting to Redis-backed buckets — per-pod in-memory limits weaken brute-force protection ×N (§7b.2).

- Add Redis SET NX locks to the three in-API schedulers (attendance IGA, access-request expiry, connector health) or move them to the worker (§7b.3).

- Verify OIDC uses the injected SAML key (isSamlEnabled() true in prod) so JWKS is identical across pods (§7b.1).

- If RADIUS UDP is needed in prod: NLB UDP Service with externalTrafficPolicy: Local; otherwise keep disabled (§7b.4).

- ServiceMonitor for /metrics; alerts on outbox queue depth and DB pool exhaustion (§11).

- Load-test a rolling deploy (maxUnavailable: 0) end-to-end, including a live login flow, before pointing DNS at the new stack.

ewpage

# PART II — Implementation Guide (Exact Changes)

Companion to HA_Kubernetes_Architecture.md. That doc explains why; this one is the exact how — code diffs against the current repo and copy-paste-ready Kubernetes/Helm YAML. Section numbers reference the architecture doc.

Assumptions: EKS with AWS Load Balancer Controller and External Secrets Operator installed, namespace idp, image pushed to ECR as <ECR_REPO>/lilg:<TAG>.

## Fix 1 — SAML + OIDC signing keys via Secrets Manager (§6, §7b.1)

Code changes: none. ensureSamlKeys() short-circuits when both env vars are set, and ensureOidcKeys() reuses the SAML key when SAML is enabled.

### 1.1 Generate the keypair once

If prod already ran on pam-2 and SPs have pinned the auto-generated cert, extract the existing one instead of generating new (avoids re-registering every SP):

# On pam-2 — pull the current auto-generated key/cert out of the container volume
docker cp idp-api:/app/data/saml/.saml-auto-keys.key ./saml.key
docker cp idp-api:/app/data/saml/.saml-auto-keys.crt ./saml.crt

Fresh install only:

openssl req -x509 -newkey rsa:2048 -nodes -sha256 \
  -keyout saml.key -out saml.crt -days 1095 \
  -subj "/CN=idp.lenskart.com/O=Lenskart IdP/OU=Identity/C=IN"

### 1.2 Store in AWS Secrets Manager

aws secretsmanager create-secret \
  --name lilg/prod/saml-signing \
  --region ap-south-1 \
  --secret-string "$(jq -n \
      --rawfile key saml.key \
      --rawfile crt saml.crt \
      '{privateKeyPem: $key, certPem: $crt}')"

# Then shred local copies
shred -u saml.key

### 1.3 Sync into the cluster (External Secrets Operator)

# k8s/externalsecret-saml.yaml
apiVersion: external-secrets.io/v1beta1
kind: ExternalSecret
metadata:
  name: lilg-saml-keys
  namespace: idp
spec:
  refreshInterval: 1h
  secretStoreRef:
    name: aws-secrets-manager        # your ClusterSecretStore/SecretStore
    kind: ClusterSecretStore
  target:
    name: lilg-saml-keys             # resulting K8s Secret
    creationPolicy: Owner
  data:
    - secretKey: SAML_IDP_PRIVATE_KEY_PEM
      remoteRef:
        key: lilg/prod/saml-signing
        property: privateKeyPem
    - secretKey: SAML_IDP_CERT_PEM
      remoteRef:
        key: lilg/prod/saml-signing
        property: certPem

### 1.4 Inject into the Deployment

# In the lilg-api container spec (full Deployment in Fix 5)
envFrom:
  - secretRef:
      name: lilg-saml-keys

### 1.5 Verify

kubectl -n idp scale deploy/lilg-api --replicas=3
# Fingerprint must be identical from every pod:
for p in $(kubectl -n idp get pods -l app=lilg-api -o name); do
  kubectl -n idp exec $p -- wget -qO- http://localhost:8080/saml/metadata \
    | grep -o '<ds:X509Certificate>[^<]*' | md5sum
done

Also check logs: no pod should print SAML auto-cert generated — if one does, the env vars didn’t reach it.

## Fix 1-ALT — Multi-client deployments WITHOUT Secrets Manager

When the same IdP is deployed for many different clients (each on their own cluster/namespace, possibly not on AWS), an external secret store per client is overhead you don’t need. The best method: an in-cluster bootstrap Job, shipped in your Helm chart, that generates the SAML keypair once per client and stores it as a plain Kubernetes Secret. No external dependency, every client automatically gets a unique cert, fully idempotent, works on any Kubernetes (EKS, AKS, GKE, on-prem).

### How it works

- Helm pre-install hook Job runs before anything else.

- If the Secret lilg-saml-keys already exists in the namespace → exit 0 (no-op on every upgrade — the cert never silently changes, which is exactly what SP fingerprint pinning requires).

- If not → generate the keypair with openssl, create the Secret, exit.

- The lilg-api Deployment consumes the Secret via envFrom exactly as in Fix 1.4 — the app’s ensureSamlKeys() short-circuit works identically. Still zero app code changes.

### 1A.1 RBAC for the bootstrap Job

# k8s/keygen-rbac.yaml
apiVersion: v1
kind: ServiceAccount
metadata:
  name: lilg-keygen
  namespace: idp
  annotations:
    "helm.sh/hook": pre-install
    "helm.sh/hook-weight": "-10"
---
apiVersion: rbac.authorization.k8s.io/v1
kind: Role
metadata:
  name: lilg-keygen
  namespace: idp
  annotations:
    "helm.sh/hook": pre-install
    "helm.sh/hook-weight": "-10"
rules:
  - apiGroups: [""]
    resources: ["secrets"]
    verbs: ["get", "create"]        # deliberately no update/delete — cert is immutable once made
---
apiVersion: rbac.authorization.k8s.io/v1
kind: RoleBinding
metadata:
  name: lilg-keygen
  namespace: idp
  annotations:
    "helm.sh/hook": pre-install
    "helm.sh/hook-weight": "-10"
roleRef:
  apiGroup: rbac.authorization.k8s.io
  kind: Role
  name: lilg-keygen
subjects:
  - kind: ServiceAccount
    name: lilg-keygen
    namespace: idp

### 1A.2 The keygen Job

# k8s/job-keygen.yaml  (Helm template — {{ .Values.idpHostname }} per client)
apiVersion: batch/v1
kind: Job
metadata:
  name: lilg-saml-keygen
  namespace: idp
  annotations:
    "helm.sh/hook": pre-install
    "helm.sh/hook-weight": "-5"          # after RBAC, before migrate Job & Deployments
    "helm.sh/hook-delete-policy": hook-succeeded
spec:
  backoffLimit: 1
  template:
    spec:
      restartPolicy: Never
      serviceAccountName: lilg-keygen
      containers:
        - name: keygen
          image: bitnami/kubectl:1.30    # has kubectl; openssl via the shell below
          command: ["/bin/bash", "-c"]
          args:
            - |
              set -euo pipefail
              NS=idp
              SECRET=lilg-saml-keys
              CN="{{ .Values.idpHostname }}"     # e.g. idp.clientname.com

              if kubectl -n "$NS" get secret "$SECRET" >/dev/null 2>&1; then
                echo "Secret $SECRET already exists — keeping existing cert (SP fingerprints stay valid)"
                exit 0
              fi

              openssl req -x509 -newkey rsa:2048 -nodes -sha256 \
                -keyout /tmp/saml.key -out /tmp/saml.crt -days 1095 \
                -subj "/CN=${CN}/O=Lenskart IdP/OU=Identity/C=IN"

              kubectl -n "$NS" create secret generic "$SECRET" \
                --from-literal=SAML_IDP_PRIVATE_KEY_PEM="$(cat /tmp/saml.key)" \
                --from-literal=SAML_IDP_CERT_PEM="$(cat /tmp/saml.crt)"

              rm -f /tmp/saml.key /tmp/saml.crt
              echo "Generated new SAML cert for ${CN}:"
              openssl x509 -in <(kubectl -n "$NS" get secret "$SECRET" -o jsonpath='{.data.SAML_IDP_CERT_PEM}' | base64 -d) -noout -fingerprint -sha256 -enddate

The Deployment consumes it exactly as before (envFrom: secretRef: lilg-saml-keys) — nothing else changes from Fix 1.

### 1A.3 Hardening plain K8s Secrets (do these since there’s no external vault)

- Enable encryption at rest for Secrets in etcd. On EKS: associate a KMS key with the cluster (one checkbox / one eksctl flag). On kubeadm: an EncryptionConfiguration with aescbc or KMS provider. Without this, Secrets are base64-plaintext in etcd.

- Restrict RBAC on the idp namespace: only the CI/CD deployer and the keygen ServiceAccount should read/write Secrets there. No cluster-wide get secrets for humans.

- Back up the Secret per client (e.g. kubectl get secret lilg-saml-keys -o yaml into the client’s encrypted backup store, or rely on etcd/Velero backups). If the namespace is deleted and recreated, a new cert gets generated and every SP for that client must re-pin — the backup is what saves you from that.

- Rotation: delete the Secret, re-run the Job (or helm upgrade after delete), then update fingerprints at that client’s SPs. Deliberate and per-client.

### If you keep per-client config in git (GitOps)

Then a generated-in-cluster Secret is invisible to git, which some teams dislike. Two well-trodden options, in order of simplicity:

- Sealed Secrets (Bitnami): generate the keypair once per client, kubeseal it against that client’s cluster, commit the SealedSecret to the client’s repo. Only that cluster can decrypt it. One controller to install per cluster.

- SOPS + age: encrypt the Secret YAML in git with a per-client age key; decrypt in the CI pipeline at deploy time. No in-cluster controller, but the CI runner holds decryption keys.

Both stay cloud-agnostic. The bootstrap-Job approach remains the recommendation when you don’t need the cert visible in git — fewer moving parts and nothing sensitive ever leaves the cluster.

### Same pattern for the app secrets

SESSION_SECRET can be bootstrap-generated per client the same way (add --from-literal=SESSION_SECRET="$(openssl rand -base64 48)" to a similar Job). Truly external credentials (DB password, SMTP, Google/Zoho/AD adapter creds) can’t be generated — deliver those per client as a plain Secret created by your deploy pipeline (kubectl create secret ... --from-env-file=client.env), or via Sealed Secrets/SOPS as above.

## Fix 2 — Migrations as a one-shot Job + skip flag (§7, Option A)

### 2.1 Code change 1 — CLI entrypoint

New file src/db/migrate-cli.ts:

/**
 * Standalone migration runner — executed by the K8s migration Job.
 *   node dist/db/migrate-cli.js
 */
import { runMigrations } from './migrate.js';
import logger from '../utils/logger.js';

runMigrations()
  .then(() => {
    logger.info('Migrations complete');
    process.exit(0);
  })
  .catch((err) => {
    logger.fatal({ err }, 'Migrations failed');
    process.exit(1);
  });

### 2.2 Code change 2 — gate the boot-time call

In src/config.ts, add to the zod schema (near the other app-level flags):

SKIP_MIGRATIONS_ON_BOOT: z
  .string()
  .optional()
  .transform((v) => v === 'true'),

…and expose it on the returned config object (in the app block):

skipMigrationsOnBoot: parsed.SKIP_MIGRATIONS_ON_BOOT ?? false,

In src/index.ts (currently line ~308–314), wrap the existing call:

if (config.app.skipMigrationsOnBoot) {
  logger.info('SKIP_MIGRATIONS_ON_BOOT=true — migrations handled externally (K8s Job)');
} else {
  try {
    await runMigrations();
  } catch (err) {
    logger.fatal({ err }, 'Database migrations failed — refusing to start');
    process.exit(1);
  }
}

Nothing changes for pam-2 / docker-compose: the flag is unset there, behavior identical.

### 2.3 Code change 3 (defense-in-depth, §7 Option B) — GET_LOCK in migrate.ts

In runMigrations(), right after the connection retry loop succeeds (after if (!conn) throw …), replace the existing try { … } finally { await conn.end(); } body wrapper:

const LOCK_NAME = 'lilg_migrations';
const LOCK_TIMEOUT_S = 120;

const [lockRows] = await conn.query<mysql.RowDataPacket[]>(
  'SELECT GET_LOCK(?, ?) AS got', [LOCK_NAME, LOCK_TIMEOUT_S],
);
if (lockRows[0]?.['got'] !== 1) {
  throw new Error(`Could not acquire migration lock '${LOCK_NAME}' within ${LOCK_TIMEOUT_S}s`);
}

try {
  // ── existing body unchanged: ensureTrackingTable → load → apply loop ──
} finally {
  await conn.query('SELECT RELEASE_LOCK(?)', [LOCK_NAME]);
  await conn.end();
}

### 2.4 The migration Job (Helm pre-upgrade hook)

# k8s/job-migrate.yaml  (Helm template — for raw kubectl, drop the annotations
# and apply this before the Deployment manifests)
apiVersion: batch/v1
kind: Job
metadata:
  name: lilg-migrate
  namespace: idp
  annotations:
    "helm.sh/hook": pre-install,pre-upgrade
    "helm.sh/hook-weight": "0"
    "helm.sh/hook-delete-policy": before-hook-creation
spec:
  backoffLimit: 2
  activeDeadlineSeconds: 600
  template:
    spec:
      restartPolicy: Never
      containers:
        - name: migrate
          image: <ECR_REPO>/lilg:<TAG>          # same image as the app
          command: ["node", "dist/db/migrate-cli.js"]
          envFrom:
            - configMapRef: { name: lilg-config }
            - secretRef:    { name: lilg-app-secrets }   # DB creds etc.
          resources:
            requests: { cpu: 100m, memory: 256Mi }
            limits:   { memory: 512Mi }

Argo CD equivalent: replace the Helm annotations with argocd.argoproj.io/hook: PreSync and argocd.argoproj.io/hook-delete-policy: BeforeHookCreation.

## Fix 3 — Redis-backed rate limiting (§7b.2)

Replace the in-memory Map in src/auth/rate-limit.ts with an atomic Redis fixed-window counter (INCR + PEXPIRE). The function signature is unchanged, so no caller changes anywhere. Reuses the shared client from session-store.ts.

/**
 * Redis-backed rate limiter for /auth endpoints — cluster-safe across pods.
 * Falls open (allows the request) if Redis is unreachable: an IdP hard-down
 * because the rate limiter can't reach Redis is worse than one unthrottled window.
 */
import { Request, Response, NextFunction } from 'express';
import { redis } from './session-store.js';
import logger from '../utils/logger.js';

// Atomic INCR + set-expiry-on-first-hit
const LUA = `
  local c = redis.call('INCR', KEYS[1])
  if c == 1 then redis.call('PEXPIRE', KEYS[1], ARGV[1]) end
  local ttl = redis.call('PTTL', KEYS[1])
  return {c, ttl}
`;

export function rateLimit(opts: { max: number; windowMs: number; keyFn?: (req: Request) => string }) {
  const { max, windowMs } = opts;
  const keyFn = opts.keyFn ?? ((req: Request) => req.ip ?? 'unknown');

  return (req: Request, res: Response, next: NextFunction): void => {
    void (async () => {
      const key = `idp:rl:${keyFn(req)}`;
      try {
        const [count, pttl] = (await redis.eval(LUA, 1, key, String(windowMs))) as [number, number];
        if (count > max) {
          const retry = Math.max(1, Math.ceil(pttl / 1000));
          res.set('Retry-After', String(retry));
          res.status(429).json({ error: 'Too many requests', retryAfter: retry });
          return;
        }
        next();
      } catch (err) {
        logger.warn({ err }, 'Rate limiter Redis error — failing open');
        next();
      }
    })();
  };
}

Notes: - Fixed-window (matches current semantics closely enough for login throttling). If you later want sliding-window, swap the Lua for a ZSET version — callers still don’t change. - Existing per-pod limits were effectively max × N; after this change the configured max is global again. Review the configured values in the /auth routes — they may have been tuned (implicitly) to single-instance behavior.

## Fix 4 — Distributed locks for the three in-API schedulers (§7b.3)

One small shared helper, then a 2-line change per scheduler. Pattern is identical to the outbox worker’s existing leader election.

### 4.1 New file src/utils/sched-lock.ts

/**
 * Best-effort distributed mutex for scheduler ticks (Redis SET NX PX).
 * Lock auto-expires; we deliberately do NOT release early, so a tick
 * runs at most once per TTL window across all pods.
 */
import { redis } from '../auth/session-store.js';
import logger from '../utils/logger.js';

export async function withSchedLock(
  name: string,
  ttlMs: number,
  fn: () => Promise<void>,
): Promise<void> {
  const key = `idp:sched:${name}:lock`;
  try {
    const ok = await redis.set(key, `${process.env['HOSTNAME'] ?? 'pod'}:${Date.now()}`, 'PX', ttlMs, 'NX');
    if (ok !== 'OK') return;              // another pod owns this tick
  } catch (err) {
    logger.warn({ err, name }, 'Sched lock: Redis unavailable — running tick locally (may duplicate)');
  }
  await fn();
}

### 4.2 Apply to each scheduler

src/services/attendance-iga/scheduler.ts — wrap the tick body (TTL = 55s, just under the 60s interval):

import { withSchedLock } from '../../utils/sched-lock.js';

timer = setInterval(() => {
  void withSchedLock('attendance-iga', 55_000, tickAll);
}, 60_000);

src/services/access-request-expiry.ts (interval 5 min → TTL 4.5 min):

import { withSchedLock } from '../utils/sched-lock.js';

timer = setInterval(() => {
  void withSchedLock('access-request-expiry', 270_000, sweep);
}, INTERVAL_MS);

src/services/connector-health.ts (TTL = interval − 10%):

import { withSchedLock } from '../utils/sched-lock.js';

healthTimer = setInterval(() => {
  void withSchedLock('connector-health', Math.floor(HEALTH_INTERVAL_MS * 0.9), tick);
}, HEALTH_INTERVAL_MS);

Also wrap the immediate boot-time invocations (void tickAll() at scheduler start, the 15s-delayed first sweep) the same way, otherwise every pod still runs once at startup.

## Fix 5 — Kubernetes manifests (compute tier, §3)

### 5.1 ConfigMap + app Secret

# k8s/configmap.yaml
apiVersion: v1
kind: ConfigMap
metadata: { name: lilg-config, namespace: idp }
data:
  NODE_ENV: "production"
  PORT: "8080"
  PUBLIC_BASE_URL: "https://idp.lenskart.com"
  SAML_IDP_BASE_URL: "https://idp.lenskart.com"
  SAML_IDP_ENTITY_ID: "https://idp.lenskart.com/saml/metadata"
  COOKIE_SECURE: "true"
  TRUST_PROXY: "true"
  SKIP_MIGRATIONS_ON_BOOT: "true"          # Fix 2 — Job owns migrations
  DB_HOST: "<rds-endpoint>.ap-south-1.rds.amazonaws.com"
  REDIS_URL: "rediss://<elasticache-endpoint>:6379/0"
  SQS_HRMS_EVENTS_URL: "https://sqs.ap-south-1.amazonaws.com/<acct>/hrms-events"
  SQS_CELERY_BROKER_URL: "https://sqs.ap-south-1.amazonaws.com/<acct>/celery-broker"

# k8s/externalsecret-app.yaml — everything else from .env that is sensitive
apiVersion: external-secrets.io/v1beta1
kind: ExternalSecret
metadata: { name: lilg-app-secrets, namespace: idp }
spec:
  refreshInterval: 1h
  secretStoreRef: { name: aws-secrets-manager, kind: ClusterSecretStore }
  target: { name: lilg-app-secrets, creationPolicy: Owner }
  dataFrom:
    - extract:
        key: lilg/prod/app        # JSON secret: DB_USER, DB_PASSWORD, SESSION_SECRET,
                                  # MASTER_ADMIN_*, INTERNAL_TOKEN, adapter creds, SMTP, …

### 5.2 ServiceAccount with IRSA (SQS + Secrets Manager)

apiVersion: v1
kind: ServiceAccount
metadata:
  name: lilg
  namespace: idp
  annotations:
    eks.amazonaws.com/role-arn: arn:aws:iam::<acct>:role/lilg-prod
    # IAM role policy: sqs:SendMessage/ReceiveMessage/DeleteMessage on the two queues,
    # secretsmanager:GetSecretValue on lilg/prod/* (app-level reads, if used at runtime)

### 5.3 lilg-api Deployment + Service

apiVersion: apps/v1
kind: Deployment
metadata:
  name: lilg-api
  namespace: idp
spec:
  replicas: 3
  strategy:
    rollingUpdate: { maxUnavailable: 0, maxSurge: 1 }
  selector:
    matchLabels: { app: lilg-api }
  template:
    metadata:
      labels: { app: lilg-api }
    spec:
      serviceAccountName: lilg
      terminationGracePeriodSeconds: 35     # index.ts forces exit at 30s
      topologySpreadConstraints:
        - maxSkew: 1
          topologyKey: topology.kubernetes.io/zone
          whenUnsatisfiable: ScheduleAnyway
          labelSelector:
            matchLabels: { app: lilg-api }
      containers:
        - name: api
          image: <ECR_REPO>/lilg:<TAG>
          ports:
            - { containerPort: 8080, name: http }
          envFrom:
            - configMapRef: { name: lilg-config }
            - secretRef:    { name: lilg-app-secrets }
            - secretRef:    { name: lilg-saml-keys }     # Fix 1
          startupProbe:                                   # covers slow first boot
            httpGet: { path: /readyz, port: 8080 }
            periodSeconds: 5
            failureThreshold: 36          # up to 3 min
          readinessProbe:
            httpGet: { path: /readyz, port: 8080 }
            periodSeconds: 10
            failureThreshold: 3
          livenessProbe:
            httpGet: { path: /healthz, port: 8080 }
            periodSeconds: 15
            failureThreshold: 3
          resources:
            requests: { cpu: 250m, memory: 512Mi }
            limits:   { memory: 1Gi }
---
apiVersion: v1
kind: Service
metadata:
  name: lilg-api
  namespace: idp
spec:
  selector: { app: lilg-api }
  ports:
    - { port: 80, targetPort: 8080, protocol: TCP }

### 5.4 PDB + HPA

apiVersion: policy/v1
kind: PodDisruptionBudget
metadata: { name: lilg-api, namespace: idp }
spec:
  minAvailable: 2
  selector:
    matchLabels: { app: lilg-api }
---
apiVersion: autoscaling/v2
kind: HorizontalPodAutoscaler
metadata: { name: lilg-api, namespace: idp }
spec:
  scaleTargetRef: { apiVersion: apps/v1, kind: Deployment, name: lilg-api }
  minReplicas: 3
  maxReplicas: 6            # keep (pool size × maxReplicas) < RDS max_connections
  metrics:
    - type: Resource
      resource:
        name: cpu
        target: { type: Utilization, averageUtilization: 65 }

### 5.5 lilg-worker Deployment

apiVersion: apps/v1
kind: Deployment
metadata:
  name: lilg-worker
  namespace: idp
spec:
  replicas: 2                     # leader-elected; 2nd is warm standby
  selector:
    matchLabels: { app: lilg-worker }
  template:
    metadata:
      labels: { app: lilg-worker }
    spec:
      serviceAccountName: lilg
      terminationGracePeriodSeconds: 35
      topologySpreadConstraints:
        - maxSkew: 1
          topologyKey: topology.kubernetes.io/zone
          whenUnsatisfiable: ScheduleAnyway
          labelSelector:
            matchLabels: { app: lilg-worker }
      containers:
        - name: worker
          image: <ECR_REPO>/lilg:<TAG>
          command: ["node", "dist/services/outbox-worker.js"]
          envFrom:
            - configMapRef: { name: lilg-config }
            - secretRef:    { name: lilg-app-secrets }
          resources:
            requests: { cpu: 100m, memory: 256Mi }
            limits:   { memory: 512Mi }

### 5.6 Ingress (ALB, TLS at the edge — §8)

apiVersion: networking.k8s.io/v1
kind: Ingress
metadata:
  name: lilg
  namespace: idp
  annotations:
    alb.ingress.kubernetes.io/scheme: internet-facing
    alb.ingress.kubernetes.io/target-type: ip
    alb.ingress.kubernetes.io/listen-ports: '[{"HTTPS":443},{"HTTP":80}]'
    alb.ingress.kubernetes.io/ssl-redirect: "443"
    alb.ingress.kubernetes.io/certificate-arn: arn:aws:acm:ap-south-1:<acct>:certificate/<id>
    alb.ingress.kubernetes.io/healthcheck-path: /healthz
    # Cloudflare stays in front: set Full (strict) mode, restrict ALB SG to Cloudflare IPs
spec:
  ingressClassName: alb
  rules:
    - host: idp.lenskart.com
      http:
        paths:
          - path: /
            pathType: Prefix
            backend:
              service: { name: lilg-api, port: { number: 80 } }

No session-affinity annotations — sessions live in MySQL/Redis (§5); affinity would only add overhead.

### 5.7 ServiceMonitor (§11)

apiVersion: monitoring.coreos.com/v1
kind: ServiceMonitor
metadata:
  name: lilg-api
  namespace: idp
  labels: { release: kube-prometheus-stack }
spec:
  selector:
    matchLabels: { app: lilg-api }
  endpoints:
    - port: http
      path: /metrics
      interval: 30s
      headers:                       # /metrics requires the internal token
        x-internal-token: <INTERNAL_TOKEN>   # or inject via secret + relabeling

## Rollout order

- Code PR — Fixes 2 (CLI + flag + GET_LOCK), 3 (rate limit), 4 (scheduler locks). All backward-compatible: with no new env vars set, behavior on pam-2 is unchanged except rate limiting moves to Redis (verify Redis reachability there) and scheduler ticks take a Redis lock (single instance → always wins the lock).

- AWS — RDS Multi-AZ + ElastiCache provisioned; secrets created (1.2); IRSA role.

- Cluster — ESO secret stores, ConfigMap/ExternalSecrets, migration Job, Deployments, PDB/HPA, Ingress, ServiceMonitor — in that order.

- Verify at 3 replicas: identical SAML fingerprint from every pod (1.5); one Applying migration log line total per migration (Job only); 429s enforced globally (hit /auth/login >max times split across pods); exactly one Attendance IGA scheduled run per due window across all pods.

- Cutover — point Cloudflare at the ALB; keep pam-2 warm until soak completes.